## Blad1
Overview of Club 5 joint research projects / updated Jan., 2013 |  |  |  | Green = Completed and closed | Yellow = Completed, but not fully reported.
| 2009 call | Project leader | Institute | E-mail | Participating institutes | Start | Duration | End | Status | Reports | Follow-up
club 5 2009-1 | Implementation and harmonisation of diagnostic tools for Coxiella burnetii (Q-fever) in cattle, goats and sheep | Anna Aspán | SVA | anna.aspan@sva.se |  | 2009-09-01 |  | 2011-02-01 | Completed. Final report received. | Elodie Rosset. Oral final report AM 2011
club 5 2009-2 | Improving diagnostics for safer surveillance of porcine brucellosis | Gregers Jungersen | DTU | grju@vet.dtu.dk |  | 16 march 2010 | 18 months |  | Completed.Final report received. | Gregers Jungersen. Intermediate report AM 2011.
club 5 2009-3 | Epizootic ulcerative syndrome. Development and implementation of diagnostic methods | Olga Haenen | CVI | olga.haenen@wur.nl |  | 2010-01-01 |  | july 1st 2011 | Completed. Final report received. | Olga Haenen. Oral final report AM 2011
club 5 2009-4 | Tularemia improved diagnostics | Dolores Gavier-Widen | SVA | dolores@sva.se |  | 2009-09-01 | 18 months | 2011-02-28 | Completed. Final report received. | Oral final report presented at AM 2011.
2010 call
club 5 2010-1 | Development of common and generic Hepatitis E viruses detection methods | Frederic Widen | SVA | frederik.widen@sva.se |  | sept 27 th 2010 |  | aug 30th 2011 | Completed. Final report received. | Nicole Pavio at ANSES. Oral final report AM 2011
club 5 2010-2 | Whole Genome PCR Scanning Characterization of C. burnetii: an approach to identify molecular and virulence markers | Karim Sidi-Boumedine | ANSES | karim.sidi-boumedine@anses.fr |  | 2010-09-01 | 18 months |  | Completed. Final report received 130131 | Karim Sidi-Boumedine. Oral intermediate report AM 2011. Oral final report AM 2012.
club 5 2010-3 | In vitro test for BoNT/C and /D: the combination of synaptosomes and endopeptidase activity as an animal free alternative for mouse bioassay | jan langeveld | CVI | jan.langeveld@wur.nl |  | 1-oct-2010 | 1 year (1yr extension possible) | 2011-11-30 | Final report received 140206 | Jan Langeveld. Oral intermediate report AM 2011. Oral intermediate report AM 2012. | Updated 140206
2011 call
club 5 2011-1 | Harmonization and implementation of RT-PCR assay(s) for Equine Arteritis Virus. | Ruth Bouwstra | CVI | ruth.bouwstra@wur.nl | CVI, ANSES, AHVLA, SVA | September 2011 | 18 months | March 2013 | Ongoing. Project started in parallel with the EIA project. First meeting held in Oct 2011. Next meeting is planned for June 2012. We have developed a PCR for EVA that should be tested and validated by a Proficiency test performed between partners (CVI, Anses, AHVLA and SVA) by mid-2013. We have already compare PCR protocols used by the 4 different lab to check which one(s) is (are) the best in different condition (apparatus…). | Written intermdiate report presented at AM 2012. Oral presentation by Hans Aymeric of final results? at AM in Copenhagen 2013. | Updated June 2013. Request for report sent 140207
club 5 2011-2 | Implementation and harmonization of a molecular diagnostic tool for Equine Infectious Anemia | Aymeric Hans | ANSES | aymeric.hans@anses.fr | ANSES, SVA, CVI | 2011-11-01 | 18 months | May 2013 | Ongoing. Project started in parallel with the EAV project. First meeting held in Oct 2011. Next meeting is planned for June 2012. For EIA, we have selected several probes and primers sets to be validated in qRT-PCR. Then we will provide this PCR protocols to partners in order to perform a PT test to check its strength. That should be done by mid-2013 too. | Written intermdiate report presented at AM 2012. Oral presentation of final results at AM 2013 in Copenhagen (Hans Aymeric). | Updated June 2013. Request for report sent 140207
club 5 2011-3 | Cooperative refining of the BioChip microarray into a routine investigative tool to address emerging viral diseases. | Akbar Dastjerdi | AHVLA | Akbar.Dastjerdi@ahvla.gsi.gov.uk | AHVLA, CVI, ANSES, DTU | 2011-09-01 | 12 months | 2012-09-01 | Final report received 140206 | Oral intermediate report presented by Bhudipa Choudhury, AHVLA at AM 2012. Oral presentation by Glyn Hewinson? of final results at AM 2013 in Copenhagen | Updated 140206
club 5 2011-4 | Multiple detections of epizootic and zoonotic pathogens in ticks. Development of low density DNA microarrays used as new epidemiologic investigative tools. | Sara Moutailler | ANSES | sara.moutailler@anses.fr | ANSES, SVA, DTU, CVI | October 2011 | 18 months | 2013-04-01 | Completed. Final report received 2014-01-15 | Written intermdiate report presented at AM 2012. Oral presentation of results at AM 2013 in Copenhagen. | Oral presentation at AM 2014?
2012 call
club 5 2012-1 | Development and validation of alternative diagnostic tools for ASF | Willie Loeffen | CVI | Willie.Loeffen@wur.nl | CVI, ANSES, SVA, DTU, AHVLA | October 2012 | 13 months | 2013-11-01 | Internal contacts dec. 2012. We hope to finish our project in March-April 2013, so I could present our results in an oral presentation in Copenhagen. |  | Updated Dec. 2012. Request for report sent 140207
club 5 2012-2 | Sequence based characterisation of ESBL-carrying plasmids from UK, S, F and NL | Dik Mevius | CVI | dik.mevius@wur.nl | CVI, AHVLA, SVA, ANSES | October 2012 | 18 months | 2014-04-01 | Kick off meeting in October at Schiphol Airport; All partners particiated. Real start per January 2013. Update Jan. 2014: Next week Thursday there is a meeting at SVA with the partners from France, UK, NL and Sweden, to talk about the results of this project. After the meeting I or we will know more about the details of the work that has been done by all partners and there we will also need to decide on sharing the information obtained in a type of clusteranalysis of all sequence data obtained. It should still be possible to report in April, but I do not know at this moment the technical problemens we may have encountered. It would be best to ask me again in early February, e.g. for the minutes of the meeting. You could also ask the Swedish colleagues involved in the project (Stefan). |  | Updated Jan. 2014
club 5 2012-3 | Bayesian statistical analysis to assess serological testing strategies for avian influenza surveillance in Europe | Marek J Slomka | AHVLA | marek.slomka@ahvla.gsi.gov.uk | AHVLA, CVI, SVA | October 2012 | 12 months | October 2013 Delayed | In brief, we have had a series of teleconferences over the past month to ensure agreement & are now commencing the work itself. January 2013 Jan. 2014: The key data from avian influenza positive flocks arrived in October 2013: This was crucial for the Bayesian analysis which has been done provisionally already with the existing data. I am currently awaiting the completion of the data from one other partner which may well help strengthen the model. I am aware of the need to write a project report, and I cc: our local AHVLA administrator accordingly. |  | Updated Jan. 2014
club 5 2012- 4 | Recommendations on future strategies for risk-based early warning and detection of known and unknown vector-borne threats |  | SVA | ann.lindberg@sva.se | SVA, AHVLA, CVI, DTU, ANSES | December 2012 | 12 months | Originally Dec. 2013 New date June 30, 2014 | Approved Sep. 2012. Kick-off by telephone conference week 51, 2012. AHVLA will deliver in March 2014, and the rest June 30, 2014. A meeting took place in Holland Oct? 2013, 2 participants. |  | Updated 131107
| 2013 call | Project leader | Institute | E-mail | Participating institutes | Start | Duration | End | Status | AM attendance | Follow-up
Club 5 2013-1 | A cost efficient field evaluated tool kit for surveillance of tick-borne pathogens in Western Europe (TickTools) | René Bødker | DTU | rebo@vet.dtu.dk | DTU, ANSES, CVI, SVA, AHVLA (to be negotiated | September 2013 | 12 months |  | Confirmed start, but not dated (140113) |  | Updated 140113
Club 5 2013-2 | Molecular epidemiology of blaCTX-M-1 plasmids in non-broilers Escherichia coli isolates from UK, Sweden and France | Jean-Yves Madec | Anses (Lyon) | Jean-Yves.MADEC@anses.fr | Anses, SVA | October 2013 | 12 months |  | Confirmed start end of November, 2013. AHVLA no longer included. CVI did not become a partner. Anses and SVA will meet in February 2014. |  | Updated 140131
Club 5 2013-3 | Matrix-assisted laser desorption/ionization time of flight MALDI-TOF, mass spectometry for identification of bacteria in veterinary medicine | Erik Eriksson | SVA | erik.eriksson@sva.se | SVA, CVI, DTU-VET, AHVLA, NVI, SMI, Anses (observation status) | October 2013 | 12 months |  | Confirmed start and correct partners |  | Updated Jan. 2014
Club 5 2013-4 | Development and validation of molecular tools for sub-typing swine influenza viruses | Scott Reid | AHVLA | Scott.Reid@ahvla.gsi.gov.uk | DTU , ANSES, CVI, AHVLA , SVA | October 2013 | 12 months |  | Confirmed start October 2013. Confirmed correct partners. |  | Updated 140111